## G4.17
Guideline 4.17: Risk Analysis - SFMEA
Deliverable 10.5
Working Package: WP10
Creation Of new value chain Relations through novel Approaches facilitating Long-term Industrial Symbiosis
Grant Agreement No 958337

## Template SFMEA
SYMBIOSIS FAILURE MODE AND EFFECTS ANALYSIS
Democase |  |  |  | Responsibility: | [7 empty] | FMEA number:
Partner |  |  |  | Prepared by: | [7 empty] | Total Pages:
Team: | [11 empty] | FMEA Date:
TABLE 1 - FMEA TEMPLATE
General risk | ID Number | Category | Risk event | Current risk evaluation | [6 empty] | Results
General risak | ID Number |  |  | Impact | I | Likelihood | L | Detection effectiveness | D | RPN | Correction Actions | Responsible | I | L | D | RPN
TABLE 2 - Lessons learnt/ risks resolved
General risk | ID Number | Category | Risk event | Current risk evaluation | [6 empty] | Results | [5 empty] | Comments
| ID Number |  |  | Impact | I | Likelihood | L | Detection effectiveness | D | RPN | Correction Actions | Responsible | I | L | D | RPN | Comment
Risk: a situation or circumstance with a realistic likelihood of occurring and an unfavourable consequence should it occur, which could result in either financial or other loss, or in an unfavourable impact on the technical, schedule or cost performance of a process project, program, or objective.
Impact of the risk: consequences of the risk considering its effects on schedule, cost, and goals terms. Furthermore, the impact of the risk across the different partners and potential cascade effects across them.
Likelihood: how probably a risk could occur according to previous experiences or foreseen changes that can impact on the system.
Detection effectiveness: accuracy of the method to detect the risk events, covering the different aspects of the identified impacts. Furthermore, the detection effectiveness should consider the time in advance to provide a solution to the risk event, if it occurs.
RPN (risk priority number) = impact x likelihood x detection number
Correction actions= Is applied to reduce the RPN, the correction action could affect either impact, likelihood or method of detection.

## Criteria
Criteria for the evaluation of the identified risks
Punctuation | Severity (S) | Likehood (O) | Detection (D) media
5 | Schedule—Major milestone impact and > 20% impact to critical path. | Very likely to occur | There is no detection method available or knowledge that will provide an alert with enough time to plan for a contingency.
Cost—Total project cost increase > 20%.
Technical—The effect on the scope renders end item unusable.
4 | Schedule—Major milestone impact and 10% – 20% impact to critical path. | Will probably occur | Detection method is unproven or unreliable; or effectiveness of detection method is unknown to detect in time.
Cost—Total project cost increase of 10% – 20%.
Technical—The effect on the scope changes the output of the project and it may not be usable to client.
3 | Schedule—Impact of 5% – 10% impact to critical path. | Equal chance of occurring or not | Detection method has medium effectiveness.
Cost—Total project cost increase of 5% – 10%.
Technical—The effect on the scope changes the output of the project and it will require client approval.
2 | Schedule—Impact of < 5% impact to critical path. | Probably will not occur | Detection method has moderately high effectiveness.
Cost—Total project cost increase of < 5%.
Technical—The effect on the scope is minor but requires an approved scope change internally and maybe with the client.
1 | Schedule—Impact insignificant. | Very unlikely | Detection method is highly effective and it is almost certain that the risk will be detected with adequate time.
Cost—Project cost increase insignificant.
Technical—Changes are not noticeable.

## List of Examples
List of examples of potential risks |  | Different perspective to consider the IS assets during SFMEA
AREA | Failure mode
Regulation | Permits not granted
Change of local/regional administration
Introduction of new regulation
Supply Chain | Delays in purchases
Unaffordable costs increase
Low quality of feedstocks
Delays in supplies
Management | Lack of high-level decision support
Delays in management decisions
Lack of agreement on future steps (maintenance, prices, etc)
Changes in advisory board of the companies
Changes of technical staff
Changes of business focus
Mistakes in scheduling
Lack of company attention on responding the emerging risks
Mismanagement of Unplanned events
Social | Lack of social acceptance of the infrastructure
Lack of labor force / compentences for the new infrastructure
Economics | Rising prices of raw material and utilities
Bad use of resources
Lack of sales qualification
Fluctuation in market demand
Lack of investment, availavity of fundings
Communication | Lack of parnerts commitment, delays in communication
Lack of business commitment
unclear roles and responsabilities
unclear goals
Lack of communicatin channels
Circularity | Needs good coordination within the demo
Shortage of recycled materials
Shortage of used products
Inefficiency of the manufacturing process
Decrease in the sales of recycled products
Low quality of recycled materials
Switch of substitutions made of virgin feedstocks
Production | Delivery delays
Limited facility and resource which support industrial symbiosis planning process
Workers still not consistent to keep the industrial symbiosis practice on its maximal
Green Supply Chain | Lack of technological knowledge of workers
Disruption/Irregularities in supply of green virgin and/or recycled material
Lack of environmental standards and certifications such as ISO, RoHS etc.
Green quality issues in supplying
Ineffectiveness in using environmentally friendly inputs
Unskilled labour
Improper green operating procedure
Lack of green social responsibilities
Redundancy among customers for adopting the green products
Competitors approach regarding green initiatives
Used product collection irregularity
Uncertainties in secondary and returning market
Capacity and inventory related issues of reprocessing centre
Returning issues such as gate keeping and screening
Green issues while closing the loop of GSC
Lack of environment policies and regulations
Technology lag in going green policies
  Technical implementation of IS solution
  Technical difficulties for the deployment of technology
TIRL(Technical)
  Coordination activities
  Communication difficulties
  Common management procedures
ORL (Organization)
  Delay of permits
  legal barriers (ej. transport of secondary raw materials)
LRL(legal)
  Increasing costs
BRL (business)
  Facing new environmental regulation
  New environmental risk (e.g. related to transport)
EnRL (environmental)
  Lack of social acceptance
  Lack of educated labour force
SRL (social)

## General risks
ID number | General risks
1 | Difficulties in the implementation of new technologies or processes
2 | Transportation issues related to the new product
3 | Pollutants in waste streams exceeding established thresholds
4 | Confidentiality concerns between parties involved in IS deployment
5 | IS activities resulting in breaches of regulatory obligations or general permit risks
6 | Unknown and/or unfavorable site conditions
7 | IS activities involving the use of a new product from another industry with associated environmental or health risks
8 | Lack of specific equipment and/or properly trained employees to manage incoming waste
9 | Lack of employees with the necessary skills and knowledge to develop these initiatives
10 | Lack of trust in the receiving company
11 | Lack of commitment and collaborative mindset to join the network
12 | Project management issues
13 | Changes in management or technical teams within a company
14 | Poor data management by companies
15 | Inability to sell products or by-products as expected
16 | Inability to find clients as expected
17 | Issues with suppliers
18 | Inability to obtain a critical input in the required quantity and/or time
19 | Financial risks
20 | Lack of procedures to ensure the viability of IS activities